## Project to profit
80.10.010 Develop program charter | _8010010DevelopProgramCharter
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Program Manager | Strategize | Initiate the process
P200 | Define Program Objectives | P300 |  | Task | Program Manager | Strategize | Outline the goals and objectives of the program
P300 | Identify Stakeholders | P400 |  | Task | Program Manager | Strategize | List all stakeholders involved in the program
P400 | Develop Program Scope | P500 |  | Task | Program Manager | Strategize | Define the scope of the program
P500 | Establish Program Budget | P600 |  | Task | Program Manager | Strategize | Determine the budget for the program
P600 | Define Program Timeline | P700 |  | Task | Program Manager | Strategize | Set the timeline for the program
P700 | Review and Approve Charter | P800 |  | Task | Program Manager | Strategize | Review the program charter and get approval from stakeholders
P800 | End |  |  | End | Program Manager | Strategize | Complete the process
80.10.200 Develop project management strategy | _8010200DevelopProjectManagementStrategy
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Strategize | Initiate the process
P200 | Define Project Management Approach | P300 |  | Task | Project Manager | Strategize | Outline the approach for managing the project
P300 | Identify Project Roles and Responsibilities | P400 |  | Task | Project Manager | Strategize | Define the roles and responsibilities of the project team
P400 | Develop Project Schedule | P500 |  | Task | Project Manager | Strategize | Create a detailed project schedule
P500 | Establish Communication Plan | P600 |  | Task | Project Manager | Strategize | Develop a plan for communication within the project team and with stakeholders
P600 | Identify Risks and Mitigation Strategies | P700 |  | Task | Project Manager | Strategize | Identify potential risks and develop strategies to mitigate them
P700 | Review and Approve Strategy | P800 |  | Task | Project Manager | Strategize | Review the project management strategy and get approval from stakeholders
P800 | End |  |  | End | Project Manager | Strategize | Complete the process
80.10.300 Develop project governance strategy | _8010300DevelopProjectGovernanceStrategy
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Governance Manager | Strategize | Initiate the process
P200 | Define Governance Structure | P300 |  | Task | Governance Manager | Strategize | Outline the governance structure for the project
P300 | Identify Governance Roles and Responsibilities | P400 |  | Task | Governance Manager | Strategize | Define the roles and responsibilities within the governance structure
P400 | Develop Decision-Making Processes | P500 |  | Task | Governance Manager | Strategize | Establish processes for decision-making within the project
P500 | Establish Reporting Mechanisms | P600 |  | Task | Governance Manager | Strategize | Develop mechanisms for reporting project progress and issues
P600 | Identify Compliance Requirements | P700 |  | Task | Governance Manager | Strategize | Identify any compliance requirements for the project
P700 | Review and Approve Governance Strategy | P800 |  | Task | Governance Manager | Strategize | Review the project governance strategy and get approval from stakeholders
P800 | End |  |  | End | Governance Manager | Strategize | Complete the process
80.10.400 Develop project approval processes | _8010400DevelopProjectApprovalProcesses
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Approval Manager | Implement | Initiate the process
P200 | Define Approval Criteria | P300 |  | Task | Approval Manager | Implement | Outline the criteria for project approval
P300 | Identify Approval Authorities | P400 |  | Task | Approval Manager | Implement | List the authorities responsible for approving the project
P400 | Develop Approval Workflow | P500 |  | Task | Approval Manager | Implement | Create a workflow for the approval process
P500 | Establish Documentation Requirements | P600 |  | Task | Approval Manager | Implement | Define the documentation required for project approval
P600 | Conduct Approval Reviews | P700 |  | Task | Approval Manager | Implement | Conduct reviews to ensure the project meets the approval criteria
P700 | Obtain Final Approval | P800 |  | Task | Approval Manager | Implement | Obtain final approval from the relevant authorities
P800 | End |  |  | End | Approval Manager | Implement | Complete the process
80.20.010 Estimate project contracts | _8020010EstimateProjectContracts
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Contract Manager | Operate | Initiate the process
P200 | Create Quote | P300 |  | Task | Contract Manager | Operate | Create the quote for the project contract
P300 | Determine Products | P400 |  | Task | Contract Manager | Operate | Determine the products for the project contract
P400 | Identify Resources | P500 |  | Task | Contract Manager | Operate | Identify the resources for the project contract
P500 | Present to Customer | P600 |  | Task | Contract Manager | Operate | Present the initial contract to the customer
P600 | End |  |  | End | Contract Manager | Operate | Complete the process
80.20.040 Negotiate project contracts | _8020040NegotiateProjectContracts
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Contract Manager | Operate | Initiate the process
P200 | Adjust Contract | P300 |  | Task | Contract Manager | Operate | Adjust the contract based on customer feedback
P300 | Review Legal Redlines | P400 |  | Task | Legal Team | Operate | Review the legal redlines in the contract
P400 | Apply Payment Terms | P500 |  | Task | Contract Manager | Operate | Apply payment terms and discounts to the contract
P500 | Obtain Customer Approval | P600,P700 | Yes,No | Decision | Contract Manager | Operate | Obtain approval from the customer
P600 | Finalize Contract | P800 |  | Task | Contract Manager | Operate | Finalize the contract
P700 | Revise Contract | P500 |  | Task | Contract Manager | Operate | Revise the contract based on feedback
P800 | End |  |  | End | Contract Manager | Operate | Complete the process
80.20.050 Finalize project contracts | _8020050FinalizeProjectContracts
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Contract Manager | Operate | Initiate the process
P200 | Conduct Final Reviews | P300 |  | Task | Legal Team | Operate | Conduct final reviews of the contract
P300 | Obtain Final Approvals | P400 |  | Task | Contract Manager | Operate | Obtain final approvals from all parties
P400 | Sign Contract | P500 |  | Task | Contract Manager | Operate | Sign the contract
P500 | Distribute Signed Contract | P600 |  | Task | Contract Manager | Operate | Distribute the signed contract to all stakeholders
P600 | End |  |  | End | Contract Manager | Operate | Complete the process
80.20.060 Maintain project contracts | _8020060MaintainProjectContracts
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Contract Manager | Operate | Initiate the process
P200 | Review Contract Changes | P300 |  | Task | Contract Manager | Operate | Review changes to the contract
P300 | Approve Changes | P400,P500 | Yes,No | Decision | Contract Manager | Operate | Approve the changes to the contract
P400 | Implement Changes | P600 |  | Task | Contract Manager | Operate | Implement the approved changes
P500 | Revise Changes | P400 |  | Task | Contract Manager | Operate | Revise the changes based on feedback
P600 | End |  |  | End | Contract Manager | Operate | Complete the process
80.20.100 Process project change requests | _8020100ProcessProjectChangeRequests
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Submit Change Request | P300 |  | Task | Project Manager | Operate | Submit a change request for the project
P300 | Review Change Request | P400 |  | Decision | Project Manager | Operate | Review the change request
P400 | Approve Change Request | P500,P600 | Yes,No | Task | Project Manager | Operate | Approve the change request
P500 | Implement Change | P700 |  | Task | Project Manager | Operate | Implement the approved change
P600 | Revise Change Request | P400 |  | Task | Project Manager | Operate | Revise the change request based on feedback
P700 | End |  |  | End | Project Manager | Operate | Complete the process
80.20.200 Define project stakeholders | _8020200DefineProjectStakeholders
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Identify Stakeholders | P300 |  | Task | Project Manager | Operate | Identify all stakeholders for the project
P300 | Define Roles and Responsibilities | P400 |  | Task | Project Manager | Operate | Define the roles and responsibilities of stakeholders
P400 | Identify Skills Required | P500 |  | Task | Project Manager | Operate | Identify the skills required for the project
P500 | Document Stakeholder Details | P600 |  | Task | Project Manager | Operate | Document the details of all stakeholders
P600 | End |  |  | End | Project Manager | Operate | Complete the process
80.30.020 Define project scope | _8030020DefineProjectScope
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Identify Objectives | P300 |  | Task | Project Manager | Operate | Identify the objectives of the project
P300 | Define Deliverables | P400 |  | Task | Project Manager | Operate | Define the deliverables for the project
P400 | Establish Boundaries | P500 |  | Task | Project Manager | Operate | Establish the boundaries of the project
P500 | Review and Approve Scope | P600,P700 | Yes,No | Decision | Project Manager | Operate | Review and approve the project scope
P600 | Finalize Scope | P800 |  | Task | Project Manager | Operate | Finalize the project scope
P700 | Revise Scope | P500 |  | Task | Project Manager | Operate | Revise the project scope based on feedback
P800 | End |  |  | End | Project Manager | Operate | Complete the process
80.30.030 Plan projects resources | _8030030PlanProjectsResources
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Resource Manager | Operate | Initiate the process
P200 | Identify Resource Needs | P300 |  | Task | Resource Manager | Operate | Identify the resource needs for the project
P300 | Allocate Resources | P400 |  | Task | Resource Manager | Operate | Allocate the necessary resources for the project
P400 | Develop Resource Plan | P500 |  | Task | Resource Manager | Operate | Develop a resource plan for the project
P500 | Review and Approve Plan | P600,P700 | Yes,No | Decision | Resource Manager | Operate | Review and approve the resource plan
P600 | Finalize Resource Plan | P800 |  | Task | Resource Manager | Operate | Finalize the resource plan
P700 | Revise Resource Plan | P500 |  | Task | Resource Manager | Operate | Revise the resource plan based on feedback
P800 | End |  |  | End | Resource Manager | Operate | Complete the process
80.30.040 Plan project tasks | _8030040PlanProjectTasks
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Identify Tasks | P300 |  | Task | Project Manager | Operate | Identify the tasks required for the project
P300 | Sequence Tasks | P400 |  | Task | Project Manager | Operate | Sequence the tasks in the correct order
P400 | Estimate Task Duration | P500 |  | Task | Project Manager | Operate | Estimate the duration of each task
P500 | Develop Task Schedule | P600 |  | Task | Project Manager | Operate | Develop a schedule for the tasks
P600 | Review and Approve Schedule | P700,P800 | Yes,No | Decision | Project Manager | Operate | Review and approve the task schedule
P700 | Finalize Task Schedule | P900 |  | Task | Project Manager | Operate | Finalize the task schedule
P800 | Revise Task Schedule | P600 |  | Task | Project Manager | Operate | Revise the task schedule based on feedback
P900 | End |  |  | End | Project Manager | Operate | Complete the process
80.30.050 Assign project resources | _8030050AssignProjectResources
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Resource Manager | Operate | Initiate the process
P200 | Identify Available Resources | P300 |  | Task | Resource Manager | Operate | Identify the available resources for the project
P300 | Match Resources to Tasks | P400 |  | Task | Resource Manager | Operate | Match the resources to the project tasks
P400 | Assign Resources | P500 |  | Task | Resource Manager | Operate | Assign the resources to the project tasks
P500 | Review and Approve Assignments | P600,P700 | Yes,No | Decision | Resource Manager | Operate | Review and approve the resource assignments
P600 | Finalize Assignments | P800 |  | Task | Resource Manager | Operate | Finalize the resource assignments
P700 | Revise Assignments | P500 |  | Task | Resource Manager | Operate | Revise the resource assignments based on feedback
P800 | End |  |  | End | Resource Manager | Operate | Complete the process
80.30.060 Forecast project resources | _8030060ForecastProjectResources
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Resource Manager | Operate | Initiate the process
P200 | Analyze Resource Needs | P300 |  | Task | Resource Manager | Operate | Analyze the resource needs for the project
P300 | Forecast Resource Availability | P400 |  | Task | Resource Manager | Operate | Forecast the availability of resources
P400 | Develop Resource Forecast | P500 |  | Task | Resource Manager | Operate | Develop a resource forecast for the project
P500 | Review and Approve Forecast | P600,P700 | Yes,No | Decision | Resource Manager | Operate | Review and approve the resource forecast
P600 | Finalize Forecast | P800 |  | Task | Resource Manager | Operate | Finalize the resource forecast
P700 | Revise Forecast | P500 |  | Task | Resource Manager | Operate | Revise the resource forecast based on feedback
P800 | End |  |  | End | Resource Manager | Operate | Complete the process
80.30.070 Manage project budget | _8030070ManageProjectBudget
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Budget Manager | Implement | Initiate the process
P200 | Define Budget | P300 |  | Task | Budget Manager | Implement | Define the budget for the project
P300 | Allocate Funds | P400 |  | Task | Budget Manager | Implement | Allocate the necessary funds for the project
P400 | Monitor Expenditures | P500 |  | Task | Budget Manager | Implement | Monitor the expenditures for the project
P500 | Review Budget | P600,P700 | Yes,No | Decision | Budget Manager | Implement | Review the project budget
P600 | Approve Budget | P800 |  | Task | Budget Manager | Implement | Approve the project budget
P700 | Revise Budget | P500 |  | Task | Budget Manager | Implement | Revise the project budget based on feedback
P800 | End |  |  | End | Budget Manager | Implement | Complete the process
80.40.005 Govern projects | _8040005GovernProjects
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Governance Manager | Operate | Initiate the process
P200 | Establish Governance Framework | P300 |  | Task | Governance Manager | Operate | Establish the governance framework for the project
P300 | Define Governance Roles | P400 |  | Task | Governance Manager | Operate | Define the roles and responsibilities within the governance framework
P400 | Develop Governance Policies | P500 |  | Task | Governance Manager | Operate | Develop policies for governing the project
P500 | Implement Governance Policies | P600 |  | Task | Governance Manager | Operate | Implement the governance policies
P600 | Monitor Governance Compliance | P700 |  | Task | Governance Manager | Operate | Monitor compliance with the governance policies
P700 | Review and Update Governance Framework | P800 |  | Task | Governance Manager | Operate | Review and update the governance framework
P800 | End |  |  | End | Governance Manager | Operate | Complete the process
80.40.008 Control project scope | _8040008ControlProjectScope
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Define Scope Baseline | P300 |  | Task | Project Manager | Operate | Define the scope baseline for the project
P300 | Monitor Scope Changes | P400 |  | Task | Project Manager | Operate | Monitor changes to the project scope
P400 | Evaluate Scope Changes | P500 |  | Decision | Project Manager | Operate | Evaluate the impact of scope changes
P500 | Approve Scope Changes | P600,P700 | Yes,No | Task | Project Manager | Operate | Approve the scope changes
P600 | Implement Scope Changes | P800 |  | Task | Project Manager | Operate | Implement the approved scope changes
P700 | Revise Scope Changes | P500 |  | Task | Project Manager | Operate | Revise the scope changes based on feedback
P800 | End |  |  | End | Project Manager | Operate | Complete the process
80.40.020 Track project expenses | _8040020TrackProjectExpenses
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Finance Manager | Operate | Initiate the process
P200 | Record Expenses | P300 |  | Task | Finance Manager | Operate | Record the expenses for the project
P300 | Categorize Expenses | P400 |  | Task | Finance Manager | Operate | Categorize the recorded expenses
P400 | Monitor Expense Trends | P500 |  | Task | Finance Manager | Operate | Monitor trends in project expenses
P500 | Review Expense Reports | P600,P700 | Yes,No | Decision | Finance Manager | Operate | Review the expense reports
P600 | Approve Expenses | P800 |  | Task | Finance Manager | Operate | Approve the project expenses
P700 | Revise Expense Reports | P500 |  | Task | Finance Manager | Operate | Revise the expense reports based on feedback
P800 | End |  |  | End | Finance Manager | Operate | Complete the process
80.40.050 Track project time | _8040050TrackProjectTime
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Record Time Entries | P300 |  | Task | Project Manager | Operate | Record time entries for the project
P300 | Categorize Time Entries | P400 |  | Task | Project Manager | Operate | Categorize the recorded time entries
P400 | Monitor Time Utilization | P500 |  | Task | Project Manager | Operate | Monitor the utilization of project time
P500 | Review Time Reports | P600,P700 | Yes,No | Decision | Project Manager | Operate | Review the time reports
P600 | Approve Time Entries | P800 |  | Task | Project Manager | Operate | Approve the time entries
P700 | Revise Time Reports | P500 |  | Task | Project Manager | Operate | Revise the time reports based on feedback
P800 | End |  |  | End | Project Manager | Operate | Complete the process
80.40.055 Track project fees | _8040055TrackProjectFees
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Finance Manager | Operate | Initiate the process
P200 | Record Fees | P300 |  | Task | Finance Manager | Operate | Record the fees for the project
P300 | Categorize Fees | P400 |  | Task | Finance Manager | Operate | Categorize the recorded fees
P400 | Monitor Fee Trends | P500 |  | Task | Finance Manager | Operate | Monitor trends in project fees
P500 | Review Fee Reports | P600 |  | Decision | Finance Manager | Operate | Review the fee reports
P600 | Approve Fees | P800,P700 | Yes,No | Task | Finance Manager | Operate | Approve the project fees
P700 | Revise Fee Reports | P600 |  | Task | Finance Manager | Operate | Revise the fee reports based on feedback
P800 | End |  |  | End | Finance Manager | Operate | Complete the process
80.40.110 Purchase project materials | _8040110PurchaseProjectMaterials
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Procurement Manager | Operate | Initiate the process
P200 | Identify Material Needs | P300 |  | Task | Procurement Manager | Operate | Identify the materials needed for the project
P300 | Select Suppliers | P400 |  | Task | Procurement Manager | Operate | Select suppliers for the materials
P400 | Request Quotes | P500 |  | Task | Procurement Manager | Operate | Request quotes from selected suppliers
P500 | Evaluate Quotes | P600 |  | Task | Procurement Manager | Operate | Evaluate the received quotes
P600 | Approve Purchase | P700,P800 | No, Yes | Decision | Procurement Manager | Operate | Approve the purchase of materials
P700 | Revise Quotes | P600 |  | Task | Procurement Manager | Operate | Revise the quotes based on feedback
P800 | Place Order | P900 |  | Collapsed Subprocess | Procurement Manager | Operate | Place the order for materials
P900 | Receive Materials | P1000 |  | Collapsed Subprocess | Warehouse Worker | Operate | Receive the ordered materials
P1000 | End |  |  | End | Warehouse Worker | Operate | Complete the process
80.40.120 Produce project materials | _8040120ProduceProjectMaterials
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Production Manager | Implement | Initiate the process
P200 | Plan Production | P300 |  | Task | Production Manager | Implement | Plan the production of project materials
P300 | Allocate Resources | P400 |  | Collapsed Subprocess | Production Manager | Implement | Allocate resources for production
P400 | Schedule Production | P500 |  | Collapsed Subprocess | Production Manager | Implement | Schedule the production activities
P500 | Monitor Production | P600 |  | Collapsed Subprocess | Production Manager | Implement | Monitor the production process
P600 | Quality Check | P700 |  | Task | Quality Manager | Implement | Perform quality check on produced materials
P700 | Approve Materials | P800,P900 | No, Yes | Decision | Quality Manager | Implement | Approve the produced materials
P800 | Rework Production | P700 |  | Task | Production Manager | Implement | Revise the production process based on feedback
P900 | Deliver Materials | P1000 |  | Collapsed Subprocess | Production Manager | Implement | Deliver the produced materials
P1000 | End |  |  | End | Production Manager | Implement | Complete the process
80.40.140 Subcontract project work | _8040140SubcontractProjectWork
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Identify Subcontract Needs | P300 |  | Task | Project Manager | Operate | Identify the needs for subcontracting work
P300 | Select Subcontractors | P400 |  | Task | Project Manager | Operate | Select subcontractors for the project
P400 | Negotiate Contracts | P500 |  | Task | Project Manager | Operate | Negotiate contracts with selected subcontractors
P500 | Review and Approve Contracts | P600 | Yes,No | Decision | Legal Team | Operate | Review and approve the subcontractor contracts
P600 | Finalize Contracts | P800 |  | Task | Project Manager | Operate | Finalize the subcontractor contracts
P700 | Revise Contracts | P500 |  | Task | Project Manager | Operate | Revise the contracts based on feedback
P800 | Monitor Subcontractor Performance | P900 |  | Task | Project Manager | Operate | Monitor the performance of subcontractors
P900 | End |  |  | End | Project Manager | Operate | Complete the process
80.40.200 Manage project communications | _8040200ManageProjectCommunications
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Initiate the process
P200 | Develop Communication Plan | P300 |  | Task | Project Manager | Operate | Develop a communication plan for the project
P300 | Identify Stakeholders | P400 |  | Task | Project Manager | Operate | Identify the stakeholders for project communications
P400 | Define Communication Channels | P500 |  | Task | Project Manager | Operate | Define the communication channels for the project
P500 | Implement Communication Plan | P600 |  | Task | Project Manager | Operate | Implement the communication plan
P600 | Monitor Communication Effectiveness | P700 |  | Task | Project Manager | Operate | Monitor the effectiveness of project communications
P700 | Review and Update Communication Plan | P800 |  | Task | Project Manager | Operate | Review and update the communication plan
P800 | End |  |  | End | Project Manager | Operate | Complete the process
80.40.300 Manage project knowledge and documentation | _8040300ManageProjectKnowledgeAndDocumentation
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Knowledge Manager | Operate | Initiate the process
P200 | Develop Documentation Plan | P300 |  | Task | Knowledge Manager | Operate | Develop a documentation plan for the project
P300 | Identify Knowledge Assets | P400 |  | Task | Knowledge Manager | Operate | Identify the knowledge assets for the project
P400 | Create Documentation | P500 |  | Task | Knowledge Manager | Operate | Create the necessary documentation for the project
P500 | Store Documentation | P600 |  | Task | Knowledge Manager | Operate | Store the documentation in a central repository
P600 | Monitor Documentation Usage | P700 |  | Task | Knowledge Manager | Operate | Monitor the usage of project documentation
P700 | Review and Update Documentation | P800 |  | Task | Knowledge Manager | Operate | Review and update the project documentation
P800 | End |  |  | End | Knowledge Manager | Operate | Complete the process
80.50.030 Correct project transactions | _8050030CorrectProjectTransactions
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Finance Manager | Operate | Initiate the process
P200 | Identify Transaction Errors | P300 |  | Task | Finance Manager | Operate | Identify errors in project transactions
P300 | Review Transaction Errors | P400 |  | Task | Finance Manager | Operate | Review the identified transaction errors
P400 | Correct Transaction Errors | P500 |  | Task | Finance Manager | Operate | Correct the transaction errors
P500 | Validate Corrections | P600 |  | Task | Finance Manager | Operate | Validate the corrections made to the transactions
P600 | Approve Corrections | P800,P700 | Yes,No | Decision | Finance Manager | Operate | Approve the corrections
P700 | Revise Corrections | P600 |  | Task | Finance Manager | Operate | Revise the corrections based on feedback
P800 | End |  |  | End | Finance Manager | Operate | Complete the process
80.50.040 Convert projects to fixed assets | _8050040ConvertProjectsToFixedAssets
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Asset Manager | Operate | Initiate the process
P200 | Identify Project Assets | P300 |  | Task | Asset Manager | Operate | Identify the assets within the project
P300 | Evaluate Asset Value | P400 |  | Task | Asset Manager | Operate | Evaluate the value of the project assets
P400 | Approve Asset Conversion | P500,P600 | Yes,No | Decision | Asset Manager | Operate | Approve the conversion of project assets to fixed assets
P500 | Convert to Fixed Assets | P700 |  | Task | Asset Manager | Operate | Convert the project assets to fixed assets
P600 | Revise Asset Evaluation | P400 |  | Task | Asset Manager | Operate | Revise the asset evaluation based on feedback
P700 | Record Fixed Assets | P800 |  | Task | Asset Manager | Operate | Record the fixed assets in the asset register
P800 | End |  |  | End | Asset Manager | Operate | Complete the process
80.50.050 Invoice project milestones | _8050050InvoiceProjectMilestones
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Billing Manager | Operate | Initiate the process
P200 | Identify Milestones | P300 |  | Task | Billing Manager | Operate | Identify the project milestones to be invoiced
P300 | Prepare Invoice | P400 |  | Task | Billing Manager | Operate | Prepare the invoice for the identified milestones
P400 | Review Invoice | P500 |  | Task | Billing Manager | Operate | Review the prepared invoice
P500 | Approve Invoice | P600,P700 | Yes,No | Decision | Billing Manager | Operate | Approve the invoice
P600 | Send Invoice | P800 |  | Task | Billing Manager | Operate | Send the approved invoice to the customer
P700 | Revise Invoice | P500 |  | Task | Billing Manager | Operate | Revise the invoice based on feedback
P800 | End |  |  | End | Billing Manager | Operate | Complete the process
80.50.055 Invoice project transactions | _8050055InvoiceProjectTransactions
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Billing Manager | Operate | Initiate the process
P200 | Identify Transactions | P300 |  | Task | Billing Manager | Operate | Identify the project transactions to be invoiced
P300 | Prepare Invoice | P400 |  | Task | Billing Manager | Operate | Prepare the invoice for the identified transactions
P400 | Review Invoice | P500 |  | Task | Billing Manager | Operate | Review the prepared invoice
P500 | Approve Invoice | P600,P700 | Yes,No | Decision | Billing Manager | Operate | Approve the invoice
P600 | Send Invoice | P800 |  | Task | Billing Manager | Operate | Send the approved invoice to the customer
P700 | Revise Invoice | P500 |  | Task | Billing Manager | Operate | Revise the invoice based on feedback
P800 | End |  |  | End | Billing Manager | Operate | Complete the process
80.50.060 Recognize project revenue | _8050060RecognizeProjectRevenue
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Finance Manager | Operate | Initiate the process
P200 | Identify Revenue Streams | P300 |  | Task | Finance Manager | Operate | Identify the revenue streams for the project
P300 | Calculate Revenue | P400 |  | Task | Finance Manager | Operate | Calculate the revenue for the project
P400 | Review Revenue Calculations | P500 |  | Task | Finance Manager | Operate | Review the revenue calculations
P500 | Approve Revenue | P600,P700 | Yes,No | Decision | Finance Manager | Operate | Approve the revenue
P600 | Record Revenue | P800 |  | Task | Finance Manager | Operate | Record the approved revenue
P700 | Revise Revenue Calculations | P500 |  | Task | Finance Manager | Operate | Revise the revenue calculations based on feedback
P800 | End |  |  | End | Finance Manager | Operate | Complete the process
80.60.020 Monitor project status | _8060020MonitorProjectStatus
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Start of the process
P200 | Collect Data | P300 |  | Task | Project Manager | Operate | Collect data from various sources
P300 | Review Data | P400 |  | Task | Project Manager | Operate | Review and analyze the collected data
P400 | Update Status | P500 |  | Task | Project Manager | Operate | Update project status
P500 | Communicate Status | P600 |  | Task | Project Manager | Operate | Communicate status to stakeholders
P600 | End |  |  | End | Project Manager | Operate | End of the process
80.60.030 Analyze project metrics | _8060030AnalyzeProjectMetrics
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Start of the process
P200 | Identify Metrics | P300 |  | Task | Project Manager | Operate | Identify key project metrics
P300 | Collect Metrics | P400 |  | Task | Project Manager | Operate | Collect data for metrics
P400 | Analyze Metrics | P500 |  | Task | Project Manager | Operate | Analyze metrics data
P500 | Report Findings | P600 |  | Task | Project Manager | Operate | Report findings to stakeholders
P600 | End |  |  | End | Project Manager | Operate | End of the process
80.60.100 Monitor project risks | _8060100MonitorProjectRisks
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Start of the process
P200 | Identify Risks | P300 |  | Task | Project Manager | Operate | Identify potential risks
P300 | Assess Risks | P400 |  | Task | Project Manager | Operate | Assess identified risks
P400 | Mitigate Risks | P500 |  | Task | Project Manager | Operate | Develop mitigation plans
P500 | Monitor Risks | P600 |  | Task | Project Manager | Operate | Monitor risks continuously
P600 | End |  |  | End | Project Manager | Operate | End of the process
80.60.200 Manage project quality | _8060200ManageProjectQuality
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Start of the process
P200 | Define Quality | P300 |  | Task | Project Manager | Operate | Define quality standards
P300 | Implement Quality | P400 |  | Task | Project Manager | Operate | Implement quality control measures
P400 | Monitor Quality | P500 |  | Task | Project Manager | Operate | Monitor quality of deliverables
P500 | Report Quality | P600 |  | Task | Project Manager | Operate | Report quality status
P600 | End |  |  | End | Project Manager | Operate | End of the process
80.60.300 Measure project progress | _8060300MeasureProjectProgress
Process Step ID | Process Step Description | Next Step ID | Connector Label | Shape Type | Function | Phase | Alt Description
P100 | Start | P200 |  | Start | Project Manager | Operate | Start of the process
P200 | Set Milestones | P300 |  | Task | Project Manager | Operate | Define project milestones
P300 | Track Progress | P400 |  | Task | Project Manager | Operate | Track progress against milestones
P400 | Update Progress | P500 |  | Task | Project Manager | Operate | Update progress status
P500 | Communicate Progress | P600 |  | Task | Project Manager | Operate | Communicate progress to stakeholders
P600 | End |  |  | End | Project Manager | Operate | End of the process